## CCM Upgrade Tasks
Planning Tasks | Confirm
Compatablity HW supported for SW version | Y
Release Notes for Upgrade Read | y
Cisco Compatablity Matrix | Y
Unity SCCP Supported | y
3rd Party Dependanices (JTAPI / TAPI etc) | Y
CUEAC | y
CUP | y
etc.
RTMT Status, Alerts, Messages etc
Confirm Fully Ready for DR if required | y
Pre Tasks | Confirm
Confirm CCM Backup OK | Y
Take Backup off SSH Server | Y
Recovery DVDs Available? | Y
Phone Firmware Available? | Y
Rebuild DVD & Upgrade ISOs Available? | Y
Cisco Contract ID: | #0000 0001
Test Tac case nearly submitted Test | Yes
Health of CUCM | Y |  | RTMT Status, Alerts, Messages etc
Health of Drives | Y
Alerts | Y
Snapshot of Database Replication utils dbreplication runtimestate | Y
Export / Save html Default Device Targets Page | Y |  | Firefox good for this, used to compare previous and upgrade firware differences, so allow revert back to default firmware.
Upgrade Tasks
CallManager | A1 | A2 | A3 | B1 | C1
ISO Uploaded | Y | Y | Y | Y | Y
MD5sum Check | Y | Y | Y | Y | Y
Extension Mobility Off | Y | Y | Y | Y | Y
Upgrade Start Time | 16:04 | 17:57 | 18:40 | 19:45 | 21:11
Upgrade Finish Time | 17:29 | 18:21 | 19:04 | 20:19 | 21:47
Duration | 1:26 | 0:24 | 0:24 | 0:33 | 0:36
Pre Change Version Tasks
Health of CUCM | y
Snapshot of Registered Devices | y
Snapshot of Database Replication utils dbreplication runtimestate | y
Change Version Tasks
Stop EM service on all servers before Flipping
Stop CCM service on each servers before Flipping (Check CCM Group config)
Stop CCM & EM service on each Server after Server Restart (to help DB replication Speed)
Restart the CCM Service on the restarted server after DB Replicatied,
Restart EM after Cluster is fully synched.
Change Default Firmware once Publisher is upgraded and BEFORE any subscribers are 'flipped'
CallManager | A1 | A2 | A3 | B1 | C1 | Notes
Extension Mobility Off | n/a | 18:54 | 18:54 | 18:54 | 18:54
Flip Start Time | 18:58 | 19:37 | 20:16 | 20:40 | 21:11 | utils system switch-version
Ping Down Time | 19:03 | 19:40 | 20:20 | 20:43 | 21:14
Ping Back Up Time | 19:08 | 19:45 | 20:25 | 20:48 | 21:20
All Services Fully "Started" | 19:20 | 19:54 | 20:37 | 21:00 | 21:31 | Utils Service List
DB Replicated Time Complete | n/a | 20:13 | 20:50 | 21:10 | 21:50 | utils dbreplication runtimestate
CHANGE DEFAULT FIRMWARE | done 19:27
Health Check on Cluster Completed | y

## Buid Requirements
Build Requirements
Quiet Room (can be shared)
Large Desk
Minimum of 3 phones for each cluster (per engineer)
PC (see below) (per Engineer)
UCCE / CCM Installers PC
Rights
Local Admin or install rights
Installed Software
notepad++ (with compare plugin)
Putty
Cisco RTMT
7zip
TFTP server
free FTPd
Firefox
kiwi Cat Tools (if large number of branches)

## DB Replication Snapshots
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: Replication status command started at: 2012-05-14-16-11
Replication status command COMPLETED 427 tables checked out of 427
No Errors or Mismatches found.
Use 'file view activelog cm/trace/dbl/sdi/ReplicationStatus.2012_05_14_16_11_26.out' to see the details
DB Version: ccm7_1_3_32900_4
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.026 Yes Connected 0 match N/A (2) PUB Setup Completed
ACMECMA3 172.16.1.113 0.143 Yes Connected 0 match N/A (2) Setup Completed
ACMECMC1 172.18.1.111 8.43 Yes Connected 0 match N/A (2) Setup Completed
ACMECMA2 172.16.1.112 0.139 Yes Connected 0 match N/A (2) Setup Completed
ACMECMB1 172.17.1.111 0.530 Yes Connected 0 match N/A (2) Setup Completed
====
DB and Replication Services: ALL RUNNING
Cluster Replication State: Replication status command started at: 2012-05-14-16-11
Replication status command COMPLETED 427 tables checked out of 427
No Errors or Mismatches found.
Use 'file view activelog cm/trace/dbl/sdi/ReplicationStatus.2012_05_14_16_11_26.out' to see the details
DB Version: ccm7_1_3_32900_4
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.028 Yes Connected 0 match N/A (2) PUB Setup Completed
ACMECMA3 172.16.1.113 0.144 Yes Connected 0 match N/A (2) Setup Completed
ACMECMC1 172.18.1.111 6.04 Yes Connected 0 match N/A (2) Setup Completed
ACMECMA2 172.16.1.112 0.135 Yes Connected 0 match N/A (2) Setup Completed
ACMECMB1 172.17.1.111 0.533 Yes Connected 0 match N/A (2) Setup Completed
====
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: PUB SETUP Started at 2012-05-16-19-57
Setup Progress: 1 node(s) added to the replication network
Setup Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.025 Yes Connected 0 match N/A (2) PUB Setup Started
ACMECMA3 172.16.1.113 0.161 Yes Off-Line N/A DB-diff N/A (2) Waiting for Pub
ACMECMC1 172.18.1.111 7.27 Yes Off-Line N/A DB-diff N/A (2) Waiting for Pub
ACMECMA2 172.16.1.112 0.148 Yes Off-Line N/A 0 N/A (0) Waiting for Pub
ACMECMB1 172.17.1.111 0.558 Yes Off-Line N/A DB-diff N/A (2) Waiting for Pub
===
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: BATCHING SYNC Requests from nodes at: 2012-05-16-20-04
Sync Request Progress: Received 1 node requests for DB sync
Sync Request Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.025 Yes Connected 0 match N/A (2) PUB Batching Sub Req's
ACMECMA3 172.16.1.113 0.149 Yes Off-Line N/A DB-diff N/A (2) N/A
ACMECMC1 172.18.1.111 6.85 Yes Off-Line N/A DB-diff N/A (2) N/A
ACMECMA2 172.16.1.112 0.148 Yes Connected 0 match N/A (0) Setup Requested
ACMECMB1 172.17.1.111 0.533 Yes Off-Line N/A DB-diff N/A (2) N/A
===
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: BROADCAST SYNC Completed on 1 servers at: 2012-05-16-20-11
Last Sync Result: SYNC COMPLETED 0 tables sync'ed out of 427
Sync Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.026 Yes Connected 0 match N/A (2) PUB Setup Completed
ACMECMA3 172.16.1.113 0.154 Yes Connected 0 match N/A (0) Not Setup
ACMECMC1 172.18.1.111 6.74 Yes Off-Line N/A DB-diff N/A (2) Not Setup
ACMECMA2 172.16.1.112 0.158 Yes Connected 0 match N/A (2) Setup Completed
ACMECMB1 172.17.1.111 0.538 Yes Off-Line N/A DB-diff N/A (2) Not Setup
====
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: BATCHING SYNC Requests from nodes at: 2012-05-16-20-37
Sync Request Progress: Received 1 node requests for DB sync
Sync Request Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.025 Yes Connected 0 match N/A (2) PUB Batching Sub Req's
ACMECMA3 172.16.1.113 0.159 Yes Connected 0 match N/A (0) Setup Requested
ACMECMC1 172.18.1.111 7.26 Yes Off-Line N/A DB-diff N/A (2) N/A
ACMECMA2 172.16.1.112 0.151 Yes Connected 0 match N/A (2) N/A
ACMECMB1 172.17.1.111 0.640 Yes Off-Line N/A DB-diff N/A (2) N/A
=====
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: BROADCAST SYNC Completed on 2 servers at: 2012-05-16-20-44
Last Sync Result: SYNC COMPLETED 0 tables sync'ed out of 427
Sync Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.024 Yes Connected 0 match N/A (2) PUB Setup Completed
ACMECMA3 172.16.1.113 0.152 Yes Connected 0 match N/A (2) Setup Completed
ACMECMC1 172.18.1.111 6.03 Yes Off-Line N/A DB-diff N/A (2) Not Setup
ACMECMA2 172.16.1.112 0.150 Yes Connected 0 match N/A (2) Setup Completed
ACMECMB1 172.17.1.111 0.582 No Off-Line N/A ? N/A (?) Not Setup
=====
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: BATCHING SYNC Requests from nodes at: 2012-05-16-21-01
Sync Request Progress: Received 1 node requests for DB sync
Sync Request Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.026 Yes Connected 0 match N/A (2) PUB Batching Sub Req's
ACMECMA3 172.16.1.113 0.151 Yes Connected 0 match N/A (2) N/A
ACMECMC1 172.18.1.111 11.8 Yes Off-Line N/A DB-diff N/A (2) N/A
ACMECMA2 172.16.1.112 0.152 Yes Connected 0 match N/A (2) N/A
ACMECMB1 172.17.1.111 0.559 Yes Connected 0 match N/A (0) Setup Requested
===
DB and Replication Services: ALL RUNNING
Cluster Replication State: BROADCAST SYNC Completed on 3 servers at: 2012-05-16-21-08
Last Sync Result: SYNC COMPLETED 0 tables sync'ed out of 427
Sync Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.023 Yes Connected 0 match N/A (2) PUB Setup Completed
ACMECMA3 172.16.1.113 0.154 Yes Connected 0 match N/A (2) Setup Completed
ACMECMC1 172.18.1.111 6.32 Yes Off-Line N/A DB-diff N/A (2) Not Setup
ACMECMA2 172.16.1.112 0.155 Yes Connected 0 match N/A (2) Setup Completed
ACMECMB1 172.17.1.111 0.562 Yes Connected 0 match N/A (0) Setup Completed
===
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: BATCHING SYNC Requests from nodes at: 2012-05-16-21-32
Sync Request Progress: Received 1 node requests for DB sync
Sync Request Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.024 Yes Connected 0 match N/A (2) PUB Batching Sub Req's
ACMECMA3 172.16.1.113 0.152 Yes Connected 0 match N/A (2) N/A
ACMECMC1 172.18.1.111 7.12 Yes Connected 0 match N/A (0) Setup Requested
ACMECMA2 172.16.1.112 0.157 Yes Connected 0 match N/A (2) N/A
ACMECMB1 172.17.1.111 0.610 Yes Connected 0 match N/A (2) N/A
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: BROADCAST SYNC Started on 1 server(s) at: 2012-05-16-21-37
Sync Progress: 0 tables sync'ed out of 427
Sync Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.024 Yes Connected 0 match N/A (2) PUB Setting Subs
ACMECMA3 172.16.1.113 0.153 Yes Connected 0 match N/A (2) N/A
ACMECMC1 172.18.1.111 6.42 Yes Connected 0 match N/A (0) Setup in Progress
ACMECMA2 172.16.1.112 0.154 Yes Connected 0 match N/A (2) N/A
ACMECMB1 172.17.1.111 0.547 Yes Connected 0 match N/A (2) N/A
admin:
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: BROADCAST SYNC Completed on 4 servers at: 2012-05-16-21-42
Last Sync Result: SYNC COMPLETED 0 tables sync'ed out of 427
Sync Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.024 Yes Connected 0 match N/A (2) PUB Setup Completed
ACMECMA3 172.16.1.113 0.166 Yes Connected 0 match N/A (2) Setup Completed
ACMECMC1 172.18.1.111 6.56 Yes Connected 0 match N/A (0) Setup Completed
ACMECMA2 172.16.1.112 0.147 Yes Connected 0 match N/A (2) Setup Completed
ACMECMB1 172.17.1.111 0.566 Yes Connected 0 match N/A (2) Setup Completed
admin:utils dbreplication runtimestate
DB and Replication Services: ALL RUNNING
Cluster Replication State: BROADCAST SYNC Completed on 4 servers at: 2012-05-16-21-42
Last Sync Result: SYNC COMPLETED 0 tables sync'ed out of 427
Sync Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.025 Yes Connected 0 match N/A (2) PUB Setup Completed
ACMECMA3 172.16.1.113 0.125 Yes Connected 0 match N/A (2) Setup Completed
ACMECMC1 172.18.1.111 6.65 Yes Connected 0 match N/A (4) Setup Completed
ACMECMA2 172.16.1.112 0.124 Yes Connected 0 match N/A (2) Setup Completed
ACMECMB1 172.17.1.111 0.558 Yes Connected 0 match N/A (2) Setup Completed
DB and Replication Services: ALL RUNNING
Cluster Replication State: BROADCAST SYNC Completed on 4 servers at: 2012-05-16-21-42
Last Sync Result: SYNC COMPLETED 0 tables sync'ed out of 427
Sync Errors: NO ERRORS
DB Version: ccm7_1_5_34900_7
Number of replicated tables: 427
Cluster Detailed View from PUB (5 Servers):
PING REPLICATION REPL. DBver& REPL. REPLICATION SETUP
SERVER-NAME IP ADDRESS (msec) RPC? STATUS QUEUE TABLES LOOP? (RTMT) & details
----------- ------------ ------ ---- ----------- ----- ------- ----- -----------------
ACMECMA1 172.16.1.111 0.023 Yes Connected 0 match N/A (2) PUB Setup Completed
ACMECMA3 172.16.1.113 0.155 Yes Connected 0 match N/A (2) Setup Completed
ACMECMC1 172.18.1.111 12.4 Yes Connected 0 match N/A (2) Setup Completed
ACMECMA2 172.16.1.112 0.156 Yes Connected 0 match N/A (2) Setup Completed
ACMECMB1 172.17.1.111 0.572 Yes Connected 0 match N/A (2) Setup Completed